## Sprint Backlog
PB Name | Task Name | Description and details | Check Out | Status | Remaining Effort [hr]
Project Setup & Infrastructure | Environment choose and setup | Software architecture choose | Both | Done | 0
Project Setup & Infrastructure | Repository created and project architecture choose | GitHub repo create | Both | Done | 0
Project Setup & Infrastructure | Docker introduction | Docker introduction on first service | Lorenzo | Done | 0
Core Parking & Reservation Management | Implement user signin and signup operations | Allow discovering, reserving, and managing parking spots. | Kevin | Done | 0
Core Parking & Reservation Management | Introduce parkings in the system and allow drivers to see parking list | Users can search for nearby parkings | Both | Done | 0
Core Parking & Reservation Management | Allow parking reservation frontend side | Better UI Implemented | Kevin | Done | 0
Core Parking & Reservation Management | Create APIs for manage parkings | Parking operations added | Lorenzo | Done | 0
Real-Time Sensor Integration & Data Pipeline | Introduce parking real time availability | Sensors data enabled | Lorenzo | Done | 0
Real-Time Sensor Integration & Data Pipeline | Introduce unique code system | Operators can now see their unique code | Lorenzo | Done | 0
Administrator Dashboard & Analytics | Introduce admin | Admin role defined | Both | Done | 0
Administrator Dashboard & Analytics | Introduce basic tickets and admin page to monitor them | User can send tickets. Admin can get info about them | Kevin | Done | 0
Administrator Dashboard & Analytics | Allow admins to see parkings and latest users registered | Admins should be able to access parking lists and latest registered users | Both | Done | 0
Administrator Dashboard & Analytics | Allow admins to edit parkings informations | Admins can edit parking information | Both | Done | 0
Support Tickets System | Allow drivers to create support tickets | Drivers can now create tickets to get support from the team | Both | Done | 0
UI/UX, Security & Refinement | Allow users to see parking history | Users can access their own reservation history | Both | Done | 0
UI/UX, Security & Refinement | Improve responsiveness and UI | The application should be Mobile responsive | Kevin | Done | 0
UI/UX, Security & Refinement | Address testing feedback and eventual bug fixes | Minor bug fixes | Both | Done | 0

## Burndown Chart
Date | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31 | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-13
Day | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42
Real | 84 | 84 | 84 | 84 | 83 | 83 | 81 | 81 | 81 | 81 | 81 | 79 | 79 | 79 | 79 | 77 | 77 | 76 | 75 | 70 | 68 | 68 | 66 | 62 | 60 | 59 | 57 | 55 | 52 | 49 | 47 | 45 | 44 | 41 | 40 | 38 | 36 | 36 | 36 | 28 | 27 | 26 | 18
Plan | 84 | 82 | 80 | 78 | 76 | 74 | 72 | 70 | 68 | 66 | 64 | 62 | 60 | 58 | 56 | 54 | 52 | 50 | 48 | 46 | 44 | 42 | 40 | 38 | 36 | 34 | 32 | 30 | 28 | 26 | 24 | 22 | 20 | 18 | 16 | 14 | 12 | 10 | 8 | 6 | 4 | 2 | 0
0 | Remaining Effort [hr]
42 | Number of days in sprint

## Product Backlog
Story Name | Story Description | Status
Project Setup & Infrastructure | Main project setup | Done
User Authentication & Authorization | Manage user registration, login, logout, and secure role-based access control (Driver, Operator, Admin). | Done
Core Parking & Reservation Management | Allow discovering, reserving, and managing parking spots. | Done
Real-Time Sensor Integration | Build the infrastructure to simulate, ingest, and process sensor data to provide live parking availability updates. | Done
User Profile & Dashboard | Allow users to view and edit their personal information, see their reservation history, and access their secure unique codes. | Done
Operator Parking Management | Allow parking operators to fully manage their fleet of parking spots (Create, Read, Update, Delete/Deactivate) and view their occupancy. | Done
Administrator Dashboard & Analytics | Provide admins with tools to view platform statistics, manage users, parkings, and monitor support tickets. | Done
Support Tickets System | Implement a microservice for creating support tickets. | Done
UI/UX & Refinement | Enhance the overall user experience by improving design and fix bugs. | Done

## Setup
Product Backlog Status Options | Spring Backlog Status Options | Development Team
Not To Do | To Do | Lorenzo
To Do | Doing | Kevin
Done | Done | Both
OK

## Change Log
Version | Date | Changes
0.1.0 | 2025-03-12 | First environment setup
0.2.0 | 2025-08-02 | BackEnd Folder Created
0.2.1 | 2025-08-06 | Navbar implemented
0.2.2 | 2025-08-06 | Sidebar implemented
0.2.3 | 2025-08-08 | Auth microservice introduced
0.3.0 | 2025-08-13 | Parking reservations introduced
0.3.1 | 2025-08-17 | HomePage Completed
0.3.2 | 2025-08-17 | Raw Login and SignUp added
0.3.3 | 2025-08-19 | About completed
0.3.4 | 2025-08-19 | Dockerfile Added
0.3.5 | 2025-08-20 | Docker introduced and first auth system implemented
0.3.6 | 2025-08-22 | Tailwind Style Added
0.4.0 | 2025-08-24 | login and signup functionalities added
0.4.1 | 2025-08-25 | Reservation feature added 1/2
0.4.2 | 2025-08-25 | Static Dependencies Set
0.4.3 | 2025-08-25 | Reservations service introduced
0.4.4 | 2025-08-25 | Parking management system introduced
0.4.5 | 2025-08-26 | Reservation service introduced in docker compose
0.4.6 | 2025-08-26 | Test parking seeds introduced
0.4.7 | 2025-08-28 | Price and type of parking implemented in db
0.4.8 | 2025-08-28 | Plate code implemented in Reservation db
0.5.0 | 2025-08-29 | Ingestion service introduced and bug fixes
0.5.1 | 2025-08-29 | Rabbitmq and Ingestion service introduced in docker compose
0.5.2 | 2025-08-30 | Random price and random parking type generator introduced
0.5.3 | 2025-08-30 | PGAdmin introduced in docker compose
0.5.4 | 2025-08-30 | Crypt and decrypt of unique code implemented and spotId renamed to parkingId
0.5.5 | 2025-08-30 | Parking information returned when asking for reservations list and user information edit api introduced
0.5.6 | 2025-08-30 | Utils folder name changed
0.6.0 | 2025-08-31 | Sensor simulator added to docker compose
0.6.1 | 2025-08-31 | getUserUniqueCode api introduced
0.6.2 | 2025-08-31 | Credentials introduced on sensor simulator
0.6.3 | 2025-08-31 | Parking simulator introduced
0.6.7 | 2025-09-01 | Sidebar profile link fixed, profile reservation added, profile edit settings added
0.6.8 | 2025-09-01 | Reservations fixed and enabled
0.6.9 | 2025-09-01 | Unique Code Added
0.7.0 | 2025-09-02 | Responsive Style redefined
0.7.1 | 2025-09-03 | Assistance tickets microservice introduced
0.7.2 | 2025-09-03 | Tickets service implemented on docker compose
0.8.0 | 2025-09-05 | Admin can now see parkings and stats
0.8.1 | 2025-09-06 | Parkings and tickets general stats implemented
0.8.2 | 2025-09-06 | Total user count stat introduced
0.8.3 | 2025-09-07 | Search parkings by operator email being admin api introduced
0.8.4 | 2025-09-07 | Get latest n users registered api introduced
0.8.5 | 2025-09-07 | Operators can now edit and add their own parking spots
0.9.0 | 2025-09-07 | Admin Dashboard created
0.9.1 | 2025-09-10 | ReservationsChecker introduced
0.9.2 | 2025-09-10 | Sensors simulator completed and default parkings defined
0.9.3 | 2025-09-12 | Total reservation price inserted in db, bug fix reservation delete and expired state
0.9.4 | 2025-09-13 | Parkings soft delete introduced
0.9.5 | 2025-09-13 | Ticket are now available through the admin dashboard
0.9.6 | 2025-09-13 | User Context Updated
1.0.0 | 2025-09-13 | Style and UX/UI Changes
1.0.1 | 2025-09-13 | Google Maps External Link added to profile page (only active reservations)